COLUMBIA PORT COMMISSION MEETING MINUTES
Date: March 20, 2025
Location: Caldwell Parish Police Jury Meeting Room

Commissioners Present:

- Darron McGuffee				Robert Frazier

- Mark Mckee					Monty Adams, Jr.

Port Director:					Guest

- Greg Richardson				Richard Smith, Terral

            - Bob Meredith, LGF

1. Call to Order:

The meeting was called to order at 11:30 AM by Chairman Darron McGuffee.

2. Adoption of Previous Meeting Minutes:

A motion was made by Mark Mckee and seconded by Bruce Frazier, Jr. to approve the minutes of the previous meeting. The motion passed unanimously.

3. Financial Report:

A motion to accept the bank statements was made by Bruce Frazier, seconded by Monty Adams, Jr., and passed unanimously.

4. Items Discussed:

4.1  New Business –

Greg requested permission to submit a grant application to Rep. Letlow and Senator Cassidy for funding to support Rail Expansion under DOT’s Community Project Funding program (earmarks).  Greg informed the board that since we have not completed the awarded earmark for the Dock, obtaining funding for a second earmark seems unlikely but we should still demonstrate our efforts to secure additional federal funding to leverage our state funds. Grant has to be submitted by March 28th

Greg discussed the full submittal of a DENR grant application which provided planning funds to assist with electrical engineering services at the Port. The grant has a ceiling of $350,000 with a 100% match.  The port needs these funds to support the electrical upgrades for the grants we have been awarded as well as information which can be used in subsequent grant applications.

4.2 Port Director's Updates:

- Greg presented the following documents:

  - Documents on the purchase of the hatten carr property along with the request for reimbursement from LaDOTD

  - Request for 1 year extension of the DHS Security Fence Project,

  - draft of DENR grant submittal,

  - Virtual Power Plant Sustainable Power Resilient Futures concept letter submitted for rural and remote areas.

  - grant application for FY25 DHS Communication Equipment no match required, and

  - Application greg assisted ORD with applying for a Rural and Tribal Assistance Pilot Program grant, the Port projects was removed from the project and META’s project in Richard Parish replaced our request for planning services.

- CV Power Tech Solar Manufacturing Facility:  Greg informed the Port Commissioners about CV Power Tech ongoing efforts to expedite their operation and they are finalizing efforts to secure final investment funding.  The award of the $10.5 million in funding to construct a 20,000 sq.ft. warehouse as well as purchase equipment and construct 4mw of solar panels will strengthen these efforts.

- Louisiana Green Fuels (LGF) Project Update: Bob Meredith address the commissioners providing them with a first hand account of the status and ongoing activities associated with the project.  As well as provided the commissioners with a $40,000 check to cover rent for the first quarter of 2025 as was agreed upon in December.

- FY2025 PIDP Grant Application: Greg and BHA are developing the grant application which will be a duplication of the previously mentioned earmark application.  The port will only be allowed to be awarded one of the grants however we increase our chances of securing funding the more applications we submit.

- RAISE Grant for Truck Parking Facility (TPF): The port received approval for Ladotd’s appraisers to accept Hatten Carr’s counter offer and the port purchased the property on  March 18th, paying $777,940 for the property. Greg will submit for 90% reimbursement from LaDOTD for the purchased property.  The State and FHWA had placed the project on pause during the uncertainty of federal projects.  The State has received three engineering bids for performing the engineering services associated with the project but holding off till the end of RFP’s limits to award the contract.

- Rail Project: Union Pacific requested revisions and additional information pertaining associated with surface water drainage, BHA and Hatch are currently working on modification and addressing is currently reviewing the railspur design developed by hatch and BHA.

- MARAD Dock Project:   BHA has taken the lead on the NEPA for the Dock and LGF has offered to provide the preliminary design of the proposed dock to ensure it incorporates other riverside construction activities required by LGF. The NEPA is time sensitive and needs to be completed by October 2025.

- EDA Grant & Engineering Services:   Currently waiting on EDA to provide go ahead to started engineering design of the Emergency Staging Area.

- Riverton Campground Road: Currently waiting on Progressive to mobilize to the site to complete the road.

- Security Fence Project:  Received Industrial board check for $25,000 and BHA is working on revising the permit for fence installation.

- State Infrastructure Bank  Greg provided an update on his efforts to assist the Office of Rural Development in evaluating the potential benefits of establishing a State Infrastructure Bank.

- Outstanding Grant Application

  - Capital Outlay (1) Railspur and (2) Land Purchase

  - Greg informed the board we had been selected to submit a full application for the grant to LaDENR-40101(d) Federal Formula Grant requesting $350,000 which will require a 100% match by the Port ($350,000).

4.3 Tenant Updates:

- Guerrero Farms:  Greg informed board that David has yet to plant at the Port.

- McClanahan:  McClanahan still has a balance of $3000 for 2023, and has not paid for Jan, Feb, and March 2025.

- Louisiana Green Fuels – continues to work to raise funds and spends most of its time on ensuring the Title VI well gets approved and providing responses to DOE associated with their loan application.

- Terral Riverservices –  Rock yard has been slow.

5. Approval of Invoices: Greg reviewed all outstanding invoices.

A motion to pay all outstanding bills was made by Monty Adams, Jr. and seconded by Bruce Frazier, The motion passed unanimously.

6. Adjournment:

A motion to adjourn the meeting was made by Monty Adams, Jr. and seconded by Bruce Frazier. The motion passed unanimously, and the meeting was adjourned.