The Board of Commissioners of the Bossier Levee District met in regular session on Wednesday,

May 14, 2025 at 10:00 a.m. at the Levee Board Office, 3404 Industrial Drive, Bossier City, Louisiana.

The President, Tim Larkin, called the meeting to order.

ROLL CALL PRESENT:  Commissioners – LARKIN, ALLEY, BANTLE, MONTGOMERY, MOORE & STELLY.

Staff: Mark Long, Devan Jordan, Deanna Rabb, Josh Monroe with DOTD, and counsel for the Bossier Levee

District, Daniel Baker.

ABSENT: NONE

The first order of business was the opening prayer by Commissioner Montgomery and the Pledge of

Allegiance by Commissioner Alley.

On motion by Montgomery, seconded by Alley, and unanimously passed, the Board dispensed with the reading of the minutes and approved the minutes of the regular Board Meeting previously held on April 9, 2025.

ROLL CALL:

AMENDMENT TO AGENDA:

On suggestion of the Chair to add an item to the agenda, Alley moved and Bantle seconded a motion to

add to the agenda a request to nominate someone on behalf of the BLD to fill a Board seat left vacant by a previous member’s passing on the Red River Waterway Commission. The President asked if any member of the public wished to speak on whether to add the item to the agenda and there was no request to speak.  The following Commissioners voted:

Alley	-	Yes

Bantle	-	Yes

Larkin	-	Yes

Montgomery -  Yes

Moore -         	Abstained

Stelly - 	Yes

By roll call vote with members present “yes” the motion carried unanimously and the item was added to

the agenda.

REQUESTS BY VISITORS:

The Board discussed the vacant seat and concluded to nominate one of the Bossier Levee District’s

present Commissioners, Mr. John Michael Moore to be considered for the seat with the Red River Waterway

Commission.

On motion by Alley, and seconded by Bantle, the Board voted unanimously, with the exception of Moore,

who abstained from voting for himself, issued a resolution for President, Mr. Timothy A. Larkin to draft and sign a

letter to the Governor, Mr. Jeff Landry officially nominating Mr. Moore for the open seat on the RRWC.

No comments from the public.

Mr. Ryan Estess with Raley & Associates, Inc. appeared to request approval for a permit for the Le Pointe

Subdivision near Willow Chute Bayou.

On motion by Montgomery, seconded by Alley, and on recommendation from the Applications Committee

the Board provisionally approved the permit request pending an updated final submittal. No comments from the

public. (PERMIT #2025 – 34)

Kurt Nixon with Nixon Engineering was present and discussed the Interior Levee Drainage Analysis for the

Red River accreditation: call with FEMA, reported requirements, and  noted engineer certification of existing

models, engineer review needed, and a discussion of a cost proposal needed as well.

OLD BUSINESS:

NONE

NEW BUSINESS:

The Board received the AJ Real Estate Holding Subdivision Unit No. 1 and the Le Pointe Subdivision from

the MPC to be reviewed for approvals and or the issuance of No Objection Letters.

The above plats were only provisionally approved until the Bossier Levee District obtains further

Information from the above entities.  Both plats will be administratively approved by Mr. Long once all updated

information is submitted.

The Board discussed a resolution to obtain approval for Mr. Tim Larkin, President to sign one of two drafts

for the Cooperative Endeavor Agreement between the Bossier Parish Police Jury and the Bossier Levee District.

(Previously approved 50/50 cost sharing for the bank stabilization project on the west bank of Red Chute Bayou,

not to exceed $350,000.00.)

On motion by Alley, seconded by Stelly, and on recommendation from the Applications Committee the

Board approved Mr. Larkin to sign one (3 originals) of the Cooperative Endeavor Agreements between the

Bossier Parish Police Jury and the Bossier Levee District. No comments from the public.

On motion by Bantle, seconded by Moore, the Board approved a resolution authorizing the Secretary to

transfer $300,000.00 from Huddleston/Smith Investments to the BLD operating checking account at Bonvenu Bank

for upcoming projects and future expenditures. No comments from the public.

LEVEE AND DRAINGE REPORT

Red Chute Bayou Channel Slope Repairs

- July 24, 2019 – Vicksburg Corps conducted a damage assessment of high-water damages on Red Chute Bayou; no determination as of November 11, 2019.

- December 9, 2019 – Donald Walker, Chief of Vicksburg Corps Emergency Management called and advised that the Vicksburg Corps would be providing funding for approximately 10 bank caving sites along the levee.

- December 10, 2019 – Captain Papia with the Vicksburg District made a site visit to assess the bank repair areas.

- March 30, 2020 – received letter dated March 24, 2020, from the colonel of the Vicksburg District Army Corps denying

our request for PL 84-99 funding for bank caving repairs.

- July 8, 2021 – Lanny Barfield, with the USACE Vicksburg District, advised that the Vicksburg District recently requested approval from the MVD for funding approval to repair of the sites.

- May 10, 2022 – Received an email from Craig Prestwood, Senior Project Manager, with the USACE Vicksburg District

advising that our request for bank stabilization repairs has been approved by the MVD and that they are getting ready to send

in a funding request to MVD for design and data collection.

- July 21, 2022- BLD provided a right-of-entry to Patrick White with the Vicksburg District for surveying and site assessment needed for plan design for bank stabilization repairs.

- September 12, 2022 – Soil survey for bank stabilization design started.

- October 12, 2022 – Topo survey for bank stabilization design near completion.

- May 4, 2023 - PDT meeting conducted through WEBX; major topic was discussion of unexploded ordinances within project limits. It is anticipated that the project delivery date will be in the fall of this year.

- May 11, 2023 – submitted right-of-way authorization documents to Corps. January 9, 2024 – USACE awarded a contract

for bank stabilization on (9) sites on Red Chute Bayou.

- May 2, 2024 – work delayed due to high water.

- Notice to proceed issued September 3, 2024.

- September 10, 2024 – Work began.

- January 6, 2025 - Work is substantially complete on (8) sites on BAFB; work on site (9) located south of BAFB is delayed pending relocation of an overhead powerline.

Red Chute Levee Raise Project

- Mitigation analysis for levee raise was conducted by Nixon Engineering and Dewberry Consultants.

- October 31, 2019 – Nixon Engineering delivered mitigation report.

- December 8, 2019 – Kurt Nixon and Jacob Lesue presented the board with mitigation study results.

- March 11, 2020 – Kurt Nixon submitted a revised mitigation study report with recommendations for a levee raise and mitigation.

Levee Inspection Compliance

- BLD has completed an inspection and report of deficiencies on the Red River Levee including items listed on the USACE 2019 and 2021 Levee Inspection Report.

- Work to remove encroaching items and the correction of deficiencies is ongoing.

Red River Levee Certification / Accreditation

- May 8, 2018 – sent letter to Corps requesting their services in providing new levee certification.

- February 7, 2020 – we received word from Craig McRaney with the Vicksburg Corps that the levee can be raised above

elevation of Lock and Dam 5 Road; Mr. McRaney also advised that the levee district should submit a request for a 408

permit to raise the levee in the areas with insufficient freeboard.

- February 10, 2020 – a conference call was held with several members of the Vicksburg Corps; the purpose of the call was

to seek guidance on how to expedite the permit for the levee raise and to request that the Corps provide assistance in obtaining

the permit. Very little new information was obtained from the call; the Corps did say that they would research

the Congressional Authorization for the levee to determine if any restrictions such as an additional congressional authorization would be needed to raise the levee.

- September 9, 2020 – hired Kurt Nixon to review options for levee certification.

- January 11, 2021 – held conference call with Vicksburg Corps and discussed 408 permit requirements for raising the areas with deficient free board on the Red River Levee north of Lock and Dam 5.

- March 3, 2021 – Kurt Nixon provided progress letter on status of the 408 permit.

- April 12, 2021 – conference call held with Katy Breaux and members of the Vicksburg Army Corps of Engineers to discuss

a Risk Assessment to be used for levee certification.

- April 22, 2021 – conference call with Vicksburg Corps to discuss Risk Assessment; Katy Breaux advised that the Corps has obtained funding for the Hydraulic Analysis portion of a Risk Assessment

- June 8, 2021 – spoke with Katy Breaux, Project Manager with Vicksburg Corps and she advised that work on the Hydraulic Analysis portion of the Risk Assessment should be completed by the end of July 2021.

- On August 17, 2021, Raley and Associates completed work on cross sectioning and topo survey of a 6.0-mile segment of the levee from lock and Dam 5 road north.

- January 4, 2022 – received a status update on the CORPS H&H Analysis for the Red River Levee; the H&H Analysis is complete however they are waiting on new risk assessment classification guidance before issuing a report.

- March 28, 2022 – a meeting with the Vicksburg Corps and local officials was held; Will McRae with the Vicksburg Corps Levee Safety Center presented Corps recommendations for a path forward on levee accreditation and discussed an in-depth levee risk assessment to be cost shared with the Corps and local entities; estimated cost range between $250,000.00 and $750,000.00.

- July 6, 2022 – re-submitted letter of request to the Vicksburg Army Corps of Engineers for a Semi-Quantitative Risk Assessment on the Red River Levee.

- December 13, 2022 – conference call with Will McCrae, Brandon Cummins, Lanny Barfield and other members of the Vicksburg Corps concerning the Semi-Quantitative Risk Assessment. Will McCrae advised that new guidance for evaluating

a risk assessment would be coming out in February of 2023; he advised waiting for the new guidance before starting the risk assessment.

- March 8, 2023 – Vicksburg Corps met with board and provide updates and recommendations for an NFIP Risk Assessment.

- April 29, 2023 – mailed letter of request for an Accelerated Levee Evaluation (Risk Assessment) for NFIP Purposes to the Vicksburg USACE.

- June 6, 2023 – received cost share agreement and scope of work for the levee risk assessment.

- July 12, 2023 – cost share funding in the amount of $433,000.00 was mailed to USACE this date.

- September 13, 2023 – hired Kurt Nixon to provide a cost estimate to raise an approximate 6-mile segment of the Red River Levee for the purpose of applying for capital outlay funding from the State.

- October 13, 2023 - Kurt Nixon provided a cost for raising a 6-mile segment of the Red River Levee with an estimated cost

of $10,376,768.00.

- December 12, 2023, through December 15, 2023 – Risk assessment team made field observations of the levee; also performed tabletop discussion on potential failure modes.

- July 8, 2024 - Risk assessment ongoing.

Levee Surfacing

- August 14, 2024 – levee surfacing planned on Red River Levee from levee station 2095+00 near Elm Grove to station 2239+00 near McDade Road; approximate length 2.73 miles; estimated cost $250,000.00.

- September 9, 2024 – currently working to resolve utility levee crossing conflicts.

- October 9, 2024 – Received approval for levee surfacing work between levee station 2131+75 south of Elm Grove and levee station 2239+00 near McDade. Approximate length 2.03 miles estimated cost $230,000.00. Utility conflict delaying work on 0.7-mile segment of original planned work.

- November 25, 2024 – Completed work on levee surfacing between levee station 2131+75 and 2239+00 at total cost of $244,223.25.

- December 2, 2024 - Began work on levee segment station 2095+00 to 2121+75, work completed on 12/4/24, total cost $67,641.63.

- December 20, 2024 – Contractor began work grading and compacting Red Chute Bayou Levee north of Dogwood Trail;

work completed on December 23, 2024. Cost $8,000.

Flat River Culvert Replacement

- October 9, 2024 – Requested approval to hire contractor to replace 42-inch diameter by 80-foot CMP outfall culvert on Ninock Ditch to Flat River Cut-off Ditch.

Levee and Drainage Crews

- Inspecting various construction activities near levees and drainage channels.

- Clearing Flat River to Red Chute Cut-Off upstream of Smith Road.

- Clearing over hanging limbs on drainage channels and levees.

- Cleaning outfall drainage culverts.

- Herbicide application on drainage channels and levees.

- Inspecting levees, channels, and drainage structures.

- Made repairs to actuators on Red Chute Bayou Diversion Structure.

- Servicing and repairing equipment.

Equipment Purchases

- July 11, 2024 – Ordered two 16-yard dump trucks. Expected delivery is February 2025.

Surplus Equipment

- The following equipment is to be sold as surplus.

- 2003 Case MX 110 with 5313 hours; Equipment # 205.

- 2016 John Deere 6135E with 520 hours; Equipment # 380.

- 2016 John Deere 6135E with 326 hours; Equipment # 381.

- 2009 John Deere 7230 with 4975 hours; Equipment # 207.

- 2009 John Deere 7230 with 4705 hours: Equipment # 208.

- 2007 Ford F-450 with 103,566 miles; Equipment # 108.

- 2000 John Deere Track Excavator with 4790 hours; Equipment # 203.

On motion by Montgomery, seconded by Stelly, and unanimously approved, the Board authorized the

secretary on behalf of the Bossier Levee District to process all payments in the amount of $142,433.57 as set

forth in the materials provided for the Board. The Board Meeting was adjourned at approximately 10:45 a.m.

_________________________			_________________________

Timothy A. Larkin, President		                        Deanna S. Rabb, Secretary