Attachment C – Specifications
RFx 3000026844

[bookmark: _Hlk150428997]Scope of Work
The Contractor shall supply all labor, rentals, permits and materials to remove and replace the front entrance apron for the Department of Corrections (DOC).

Location:
Elayn Hunt Correctional Center
6925 Highway 74
Saint Gabriel, LA 70776

Site Visit Contact:
Randy Henderson,  Keith.Henderson@la.gov, 225-716-3263

Specifications:
The Contractor shall be responsible for the following:
Demolish and Temporary Limestone Drive:
· Set advance warning signs and barricades in accordance with the plans and as directed by the engineer.

· Sawcut and remove existing asphalt pavement, base course, and limestone of the drive, as shown in the plans.

· Temporarily remove existing light poles. Prior to placement of base material. Install a plywood cover over the existing foundation. Drill holes in the plywood as necessary to accommodate the exposed anchor bolts so that the plywood sits flush with the top of the anchor bolts.

· Install temporary bollards to protect the existing entrance sign on the west side of the drive.

· Lay down geotextile fabric where the concrete paving improvements will take place.

· Lay down 8” 610 limestone for temporary drive and proposed base for 8” concrete pavement.

Phase 1:
· Install barricades to protect the work area on the left side of the drive.

· Lay 4” conduit and install right pull box (east side) as indicted in the plans. Pull box to be fiberglass reinforced underground enclosure with removable cover, traffic rated H20-44.

· Pour 8” reinforced high early strength (H.E.S) Portland cement concrete pavement.

· Cut pavement joints to match plans.

Phase 2:
· Relocate work zone devices to the opposite side of the drive.

· Verify the aggregate scarified, recompacted, and restored to a minimum compaction thickness of 8”.

· Pour 8” reinforced high early strength (H.E.S) Portland cement concrete pavement.

· Cut pavement joints to match plans.

Phase 3 and Cleanup:
· Remove temporary limestone drive on west side of newly constructed drive.

· Install the left pull box (west side) indicated in the plans. Pull box to be fiberglass reinforced underground enclosure with removable cover, traffic rated H20-44.

· Remove temporary bollards near the entrance sign on the west side of the drive.

· Reinstall removed light poles on each side of the drive.

· Hydroseed any disturbed areas.

· Remove work zone devices & barricades from the site.

Terms and Conditions:
· The Designer's normal working hours are from 7:30 A.M. to 5:00 P.M. Monday through Thursday and from 7:30 A.M. to 11:30 A.M. on Friday.

· The Contractor shall be furnished free of charge four copies of the Project Manual and shall be furnished as many additional copies as he may require, at the cost of reproduction.

· Contract time shall be based on calendar days. A calendar day is one of 24 hours beginning at 12:00 midnight.

· Reasonably anticipated days of adverse weather shall not be cause for an extension of the Contract time unless such extension is agreed to in writing between the Contractor and DOC.

· The Contractor shall include verification of all necessary permits to the Designer with the first payment request.

· Payments shall be made on account of materials or equipment not incorporated in the work but delivered and suitably stored at the site, but payments shall not be made on account of materials stored off-site. Invoices may be required.
· The Contractor shall provide files and racks for storage of documents.

· Where daylight or installed project lighting, at areas to be inspected, is less than 30 candle power, the Contractor shall provide this same level by artificial illumination with portable lighting.

· Existing utility lines shall remain in continuous operation during the construction period; the Contractor shall fully cooperate with DOC to prevent interruption of essential services. All excavations should be closed by the end of the day unless specific written permission has been granted by the Designer. 

· The Contractor shall protect the safety of the public and his employees.

· The Contractor shall perform work and store materials and equipment without restricting highway or railroad access required by code, law or regulation.

· The Contractor shall restrict working force, vehicles, storage, loading and staging areas to locations that do not conflict with the traffic or facility operations.

· The Contractor shall advise DOC and obtain advance permission for any interruptions of utility and operating services.

· The Contractor shall keep all necessary plans, specifications and permits for the said project on the jobsite at all times. The Contractor is also responsible for the same if they have any Subcontractors.

· The Contractor shall confine loose materials, papers, trash, and debris to prevent scattering. The Contractor shall transport in covered carts or receptacles to prevent the spread of dust and dropping of materials.

· The Contractor shall use canvas or rubber blankets to eliminate the spread of sparks while welding.

· The Contractor shall always have adequate fire extinguishers available and readily accessible at work areas.

· Care shall be taken not to remove, disturb or injure existing utilities, pipes or conduits during excavation, backfilling and installing pipe without the approval of the Designer.  If necessary, the Contractor shall shore up, sling and maintain any of these structures during work operation and shall repair all damage done to same within a reasonable length of time after damage (within 24 hours). All repairs shall be made to the satisfaction of the Designer.



· If at any time utilities are damaged during progress of work, the Contractor shall notify the proper authority without delay and shall at his option repair the damage if approved by the utility agency done to such structures or pay to the utility the amount required to make proper repairs for such damage. The Contractor shall be responsible for any damage done to persons or property due to damaged structures or his neglect in reporting and/or repairing damaged structures.

· DOC or the Designer shall not be responsible for any claims the Contractor may have based on underground obstructions being different than shown on the Plans. The Contractor shall, when directed to do so by the Designer, uncover subsurface obstructions before the work reaches them.  

· Requirements and practices shall not be limited to items described herein.  Compliance with these items shall not relieve the Contractor of responsibility for providing additional safety or warning devices as job conditions or construction phasing may require.

· Existing chemical lines shall be tapped and run above ground until new lines are operational by the Contractor.

· Any work which requires temporary suspension of utilities or treatment shall be coordinated with the project Designer and the facility staff.  A minimum of 48 hours’ notice is required.

· The Contractor shall expedite work to minimize interference with continuing facility operations.

· Work at other than normal hours and days (whether for the Contractor's convenience, to meet schedule requirements, or due to Owner's requirements) shall be arranged for and scheduled in advance with Owner's approval.  No extension of time and no additional compensation will be allowed for additional costs due to work at other than normal times.

· The Contractor shall cooperate with DOC’s security staff in maintaining security throughout the construction period.

· The Contractor shall be solely responsible for security of his temporary facilities, storage areas, equipment and other construction means.

· The Contractor shall construct and maintain temporary fences and gates, if necessary, for construction as indicated or required.




· Throughout the construction period, the Contractor shall have on call, 24 hours a day and 7 days a week, a responsible representative with authority to act immediately in emergencies involving life safety.  The name and telephone number of this representative shall be kept on file with the facility.

· DOC will engage and pay for the services of an independent testing laboratory to perform inspection and tests of materials and construction except that in the event of a test failure, the Contractor shall pay for re-testing. Types and extent of testing are specified in detail in applicable Sections of the Specifications.

· The Contractor shall cooperate with the laboratory.

· Make available, without cost, samples of all material to be tested in accordance with applicable standard specifications.

· The Contractor shall furnish such nominal labor and shelter working space as is necessary to obtain samples at the Project Site.

· The Contractor shall advise the laboratory of the identity of material sources and instruct suppliers of required tests or inspections by designated laboratory.

· The Contractor shall notify the laboratory sufficiently in advance of operations to allow for completion of initial tests and assignment of inspection personnel (minimum 48 hours’ notice).

· The Contractor shall notify the laboratory sufficiently in advance of cancellation of required testing operations. The Contractor shall be responsible to the laboratory for charges due to failure to notify if requirements for testing are canceled.

· The laboratory shall notify the Contractor of any materials which are not in full conformance with the Specifications.  The Designer shall be informed of such notifications.

· Tests and inspections shall be conducted in accordance with the requirements of these Specifications, or where no specific procedure is specified, in accordance with the latest standards of ASTM or other recognized authorities applicable to the work being tested.

· The laboratory shall promptly submit written reports of each test and inspection made to the Designer, Contractor, DOC and to such other parties the Designer or DOC may specify.




· The Designer shall recommend to DOC the type and number of tests to be performed on the Project. The Contractor will be advised of the number and type of tests to be performed by the Testing Laboratory, if different than specified in the various Sections of these Specifications.

· Testing Laboratory Services are required for the following items:
· Excavation, Filling and Grading
· Cast-In-Place Concrete

· The Contractor is responsible for testing laboratory costs necessary to confirm concrete mixes to be used where specified in plans.

· Concrete cylinders shall be required as requested by the Designer and paid for by DOC.

· Locate temporary facilities and signs in designated areas to avoid interfering with facility operations. All locations of temporary facilities must be approved by facility staff prior to beginning construction.

· Staging Area: The Contractor and Subcontractors shall locate offices, materials storage and staging, equipment storage and maintenance areas, and similar major facilities in a staging area which does not interfere with operations required under the contract.

· For exterior storage, the Contractor shall provide suitable and sufficient enclosed covered structures with raised flooring, to protect materials and equipment subject to damage by weather or construction work.

· The Contractor shall provide weatherproof coverage for materials and equipment needing only limited protection.

· The Contractor shall allocate and designate storage areas and workspaces for various trades.

· The Contractor shall arrange temporary buildings and designate storage spaces to avoid interfering with operations, to avoid re-handling and to expedite progress of work.

· Signs, as necessary for safety and to meet insurance requirements shall be required.

· Signs, other than those specified, will not be permitted on site without specific approval.



Fencing, Barricading and Safety Equipment

· The Contractor shall construct and maintain, until construction is completed and accepted, fences, barricades and other necessary items required to prevent injury to persons on or about Project site, damage to property and intrusion of unauthorized persons.  
· The Contractor shall provide personal safety equipment for authorized visitors.

· The Contractor shall protect structures, utilities, sidewalks, pavements, and other facilities immediately adjacent to excavations from damage or displacement.

· The Contractor shall be responsible for always maintaining access during construction for the facility.

· The Contractor shall provide adequate temporary toilet facilities for use of persons working at site, as determined by size of work force on site and Local Sanitary Code Requirements.

· The Contractor shall maintain toilets in a clean and sanitary condition. The Contractor shall provide toilet tissue in suitable holder. The Contractor shall provide natural or artificial light and ventilation to toilet compartments.

· The Contractor shall remove temporary toilets when construction is completed and accepted.

· It shall be the responsibility of the Contractor to determine a source for electric power to be used for construction purposes, and to plan, pay deposits, furnish and install equipment, poles, wiring, switches and outlets to provide adequate supply of electricity for lighting and power during construction. Meet applicable safety requirements.

· The Contractor shall pay all costs for providing electric service for construction purposes and shall pay for current used during construction until acceptance.

Water and Gas

· It shall be the responsibility of the Contractor to determine a source of water and gas service to be used for construction purposes and to make arrangements, pay deposits, furnish and install equipment, piping, valves, outlets and hoses to provide construction water and gas during construction period.

· The Contractor shall pay all costs for water and gas service for construction purposes and shall pay all costs for water and gas used during construction until acceptance.


· The Contractor shall provide cold water and paper cups for drinking for project workers.

Pumping and Draining
· The Contractor shall keep working and storage areas free from water that could damage or that could interfere with progress of work.

· The Contractor shall slope ground to drain surface water away from excavations and structures.

· The Contractor shall pump or drain to designated points as determined by the Designer. The Contractor shall distribute discharge to prevent excessive erosion and replace eroded materials.

Trucking

· The Contractor shall load all trucks bringing materials to site or removing earth and debris from site in a manner to prevent the dropping of materials, earth or debris on public streets, roads and highways.

· The Contractor shall maintain an installation at all points where and when trucks enter or leave site to remove materials, mud or debris immediately from streets, roads and highways.

· The Contractor shall conform to all local regulations regarding load limits.

Sheet Piling

· In addition to work specified, the Contractor shall provide sheet piling, should such be found necessary.

· Type, thickness, shoring, bracing and other details regarding sheet piling shall be the Contractor's sole responsibility and shall be determined by them as necessitated by excavation depth, soil conditions, rainfall, traffic adjacent to site and other related factors.

Fire Protection

· The Contractor shall provide general temporary fire protection during construction period.

· The Contractor shall have immediately available suitable fire extinguishers in areas where welding, flame cutting, and other hazardous operations are underway.



· The Contractor shall clean area that was occupied by temporary work. The Contractor shall remove debris, rubbish and excess materials from the site daily.

· This work consists of preparatory work and operations, including those necessary for the movement of personnel, equipment, supplies and incidentals to the project site; the establishment of offices, buildings and other facilities necessary for work on the project; the cost of bonds and any required insurance; and other preconstruction expenses necessary for start of the work, excluding the cost of construction materials.

· Material and equipment incorporated into the Work:

· Conform to applicable specifications and standards.

· Comply with size, make, type and quality specified, or as specifically approved in writing by the Designer.

· Manufactured and Fabricated Products:

· Design, fabricate and assemble in accordance with the engineering and shop practices accepted as industry standard.

· Component parts of multiple items shall be interchangeable.

· Two or more items of the same kind shall be identical, by the same manufacturer.

· Products shall be suitable for the service conditions in which they will be used.

· Provide equipment in the capacities, sizes and dimensions shown or specified unless variations are specifically approved in writing.

· Do not use material or equipment for any purpose other than that for which designed or specified.

· The Contractor shall handle, install, connect, clean, condition and adjust products in strict accord with such instructions and in conformity with specified requirements.

Transportation and Handling

· The Contractor shall arrange deliveries of products in accord with construction schedules.  The Contractor shall coordinate all deliveries with the facility to avoid conflict with work and conditions at the site.


· Deliver Products in undamaged condition, in the manufacturer's original containers or packaging, with identifying labels intact and legible.

· Immediately on delivery, The Contractor shall inspect shipments to assure compliance with requirements of contract documents and approved submittals, and that products are properly protected and undamaged.

· The Contractor shall provide equipment and personnel to handle products by methods to prevent soiling and damage to products, packaging, and work in place.

Storage and Protection

· The Contractor shall store products in accord with manufacturer's instructions, with seals and labels intact and legible.

· Store products subject to damage by the elements in weathertight enclosures.

· Maintain temperature and humidity within the ranges required by manufacturer's instructions.

· Prevent soiling and staining.

· Exterior Storage

· The Contractor shall store fabricated products above the ground, on blocking or skids.  Cover products which are subject to deterioration with impervious sheet coverings, with adequate ventilation to avoid condensation.

· The Contractor shall store loose granular materials in a well-drained area on solid surfaces to prevent mixing with foreign matters.

· The Contractor shall arrange storage in a manner to provide easy access for inspection.  Make periodic inspections of stored products to assure that Products are maintained under specified conditions, and free from damage or deterioration.

· The Contractor shall store products in such a manner as to prevent damage to in-place work.

· Protection After Installation: The Contractor shall provide substantial coverings as necessary to protect installed products from damage from traffic and subsequent construction operations. The Contractor shall remove when no longer needed.

Replacement And Repair

· The Contractor shall promptly remove damaged, defective and non-conforming material and equipment and replace with new material and equipment.
· Subject to Designer's approval, damaged and defective material and equipment may be repaired to condition equivalent to acceptable new condition. Material and equipment that cannot be satisfactorily repaired shall be removed and replaced by the Contractor.

· Replacement and repairs shall be made by the party responsible for the original installation of the materials and equipment involved, without additional cost to DOC.

General Requirements

· The Contractor shall provide the services of a Registered Land Surveyor for laying out lines and establishing elevations of structures and improvements including all piping, equipment and foundation elevations.

· The Surveyor shall locate benchmarks and other reference points necessary to establish location, limits and extent of work.

· DOC requires that this project generate the least amount of trash and waste possible.

· The Contractor shall employ processes that ensure the generation of as little waste as possible due to error, poor planning, breakage, mishandling, contamination, or other factors.

· The Contractor shall minimize trash/waste disposal in landfills; reuse, salvage, or recycle as much waste as economically feasible.

· The Contractor shall submit periodic Waste Disposal Reports; all landfill disposal, incineration, recycling, salvage, and reuse must be reported regardless of to whom the cost or savings accrues; use the same units of measure on all reports.

· Methods of trash/waste disposal that are not acceptable are:
· Burning on the project site.
· Burying on the project site.
· Dumping or burying on other property, public or private.
· Other illegal dumping or burying.

· Regulatory Requirements: The Contractor is responsible for knowing and complying with regulatory requirements, including but not limited to Federal, state and local requirements, pertaining to legal disposal of all construction and demolition waste materials.

· Fire Protection: The Contractor shall store volatile waste in covered metal containers and remove from premises daily.
· Pollution Control: The Contractor shall conduct clean-up and disposal operations to comply with local ordinances and anti-pollution laws.

· Disposal of volatile fluid wastes (such as mineral spirits, oil or paint thinner) in sanitary or storm systems is not permitted.

· The Contractor shall use only cleaning materials recommended by manufacturer of surface to be cleaned.

· The Contractor shall use cleaning materials only on surfaces recommended by cleaning material manufacturer.

· The Contractor shall execute periodic cleaning of the project site to ensure that grounds and adjacent properties are maintained free from accumulation of waste material and rubbish caused by Project construction operations.

· The Contractor shall sprinkle dusty debris with water.

· During the progress of work, the Contractor shall clean-up site and dispose of waste materials, rubbish, and debris.

· The Contractor shall provide for collection of waste materials, rubbish and debris.

· The Contractor shall not allow waste materials, rubbish, debris and garbage to accumulate and become unsightly, unhealthy or hazardous.

· The Contractor shall remove waste materials, rubbish, and debris from the site and legally dispose of same at public or private dumping areas away from Project site.

· The Contractor shall broom clean paved surfaces; rake clean other surfaces of grounds.

· The Contractor shall maintain cleaning until Project or portion thereof is accepted by the Owner.

· The Contractor shall furnish all labor, materials and equipment to perform color audio-video recording of the project site surfaces as specified herein and in Section 017123 Field Engineering. The Contractor shall furnish to DOC an original and one copy of a continuous color and audio-video DVD recording of the project sites. 


· DOC reserves the right to reject the audio-video DVD because of poor quality, unintelligible audio or uncontrolled pan or zoom. Any video rejected by DOC shall be re-videoed at no additional cost to DOC. The Contractor shall submit one DVD to DOC for format and content approval prior to the start of any work. 
· Prior to the commencement of any construction, equipment or material mobilization, the Contractor shall perform an audio-video survey of each project site area which will be excavated, or which has the potential to be disturbed by the Contractor’s operations. Specific areas of this project include, but are not limited to: 
· All areas to be entered by vehicles or equipment, including construction areas for tank improvements.  
· Paved and unpaved areas which will be entered by vehicles or equipment. 
· Other areas that may be impacted by the Work, including work staging areas and field offices, as directed by the Owner. 
· Quality 
· The video recording shall be performed by a qualified audio-video taping firm or individual knowledgeable in construction practices and experienced in the implementation of established inspection procedures. 
· The video portion of the recording shall produce bright, sharp, clear pictures with accurate colors and shall be free from distortion, tearing, rolls, or any other form of picture imperfection. The audio portion of the recording shall reproduce precise and concise explanatory notes by the camera operator with proper volume, clarity and freedom from distortion. 
· The recorder shall record the video in full high definition (1080p) in common file format.  
· The Contractor shall be responsible for the timely execution of the preconstruction audio-video survey, its vantage points, and quality.  The Contractor shall cooperate with the photographer’s work and provide reasonable auxiliary services as requested, including access and use of temporary facilities including temporary lighting. 

· Qualifications
· Photographer’s Qualifications: The Contractor shall submit the name and qualifications of photographer to the engineer for review and acceptance prior to commencement of the work.  





· Deliverables
· Submitted DVDs shall be reviewed and approved by DOC within five days of submitting a satisfactory survey. Should the DVD not provide adequate coverage to fully illustrate the physical condition of the work area or not follow the specifications, project areas shall be re-surveyed prior to the initiation of construction at the project sites, with no additional cost to DOC. 
· The Contractor shall provide two copies; labeled on the DVD and jewel case cover with the following information: 
· Face of DVD & Case Cover 
· PRECONSTRUCTION AUDIO-VIDEO SURVEY
· Contract No._____________		Project Title:_____________________	 Contractor:________________________ 	DVD No.__________________	
· Date Televised (MM/YY):____________  	Date Submitted _____________

· Inside of Case Cover 
	· Work Area
	· Street, Address/Location
	· Starting Video Counter No.

	· 
	· 
	· 

	· 
	· 
	· 

	· 
	· 
	· 

	· 
	· 
	· 

	· 
	· 
	· 


· Note: The Contractor may record the surface videos of as many line segments as possible on a single DVD. 
· A cumulative index correlating the various segments of video coverage to the corresponding DVD’s shall be supplied to DOC. This index shall identify each segment in the video by location, engineering stationing corresponding to the stationing on the contract documents, video counter number, viewing side, point starting from, traveling direction, and ending point. Written documentation must coincide with the information on the tape so as to make easy retrieval of locations sought for at a later date. 

· Usage Rights 
· To preclude the possibility of tampering or editing, the DVD shall display continuous digital information including the following: 
· Date and time of the recording; date information will contain the month, day and year; time information will contain hours, minutes and seconds, separated by colons. 
· The engineering stationing corresponds to the stationing on the contract documents, or as directed by DOC. 
· Digital information shall appear at the bottom of the viewing screen and in no way interfere with the video portion of the recording. 

· Part 3 Execution
Video Recordings - General
· At the start of each video recording segment, an identification summary shall be read into the record simultaneously with a wide-angle view with digital information. The identification summary shall include the following: 
· DVD number 
· Contract number and name 
· Contractor’s name 
· Date and time 
· General location and stationing 
· Weather 
· Direction of travel and viewing direction 

· The recording shall include the coverage of all surface and other site features located in areas to be affected by the Work. The surface features recorded shall include, but not be limited to, roadways, driveways, sidewalks, curbs, culverts, headwalls, retaining walls, buildings, above-ground utilities, equipment, parks, lawns, landscaping, trees, tree canopies, shrubbery and fences. The area of coverage shall extend to 50 feet from the proposed work site but shall also include all unpaved areas and access routes where vehicles or equipment will pass.

· Video recording may be ordered outside of the area of coverage to establish those features deemed necessary by DOC. 

· Video recording coverage shall include documentation of the condition of the surface and other site features located within the area of coverage and shall be supported by appropriate audio description. Audio description shall be made simultaneously with the video recording. 

· Buildings shall be identified visually and verbally by number and or name in such a manner that proposed improvements (i.e., future grading) can be located by reference. 

· The coverage shall be continuous (i.e., the camera shall not be turned off once recording has begun) to the greatest extent possible. 

· The rate of travel for video recording shall be determined by the number, size and value of the surface and other site features within the construction area of coverage so as to produce a clear, detailed view of each feature. At no time shall the rate of travel exceed 44 feet per minute. Forward motion of the camera shall be halted when viewing objects or structures outside the limits of the street or easement being documented. 

· The photographer shall pan and zoom in and out at a reasonable rate to control sufficiently the clarity of objects being viewed. 

· When recording, the camera shall be mounted on a steady base. Horizontal and vertical shots shall be made from the base, to ensure proper perspective. The distance from the camera lens to the ground shall be not less than 12 feet. If not accessible by motorized vehicle, height shall be determined by the distance from ground to shoulder height of the camera operator. The Contractor shall furnish all auxiliary lighting as required to produce a quality recording. At no time will the Contractor be allowed to use any electrical circuits within a building on private properties. 

· All video recordings shall be performed during regular business hours, unless otherwise approved by DOC. 

· No video recording shall be performed if the weather is not acceptable, such as rain, fog, or elongated shadows that distort perception and tend to prevent clear resolution
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